Graveyard — Developer C — Frontend & Product Lead

Build guide for Frontend / Product Developer · 7-Day Timeline · Team Ignite

# Your Mission

Own the entire user-facing experience and the growth-facing surfaces (landing page, shareable cards, Product Hunt assets). Since the public launch phase depends on real people using the app, your UX quality directly determines whether Graveyard gets real traction — not just a good demo.

# Features You Own

3. 10-second reason capture (UI)

The core habit-capture flow: tap a preset tag, optional one-line text, submit in under 10 seconds. This has to be frictionless — it's the single UX decision the whole product's data quality depends on.

6. Pattern dashboard

The main screen: stats + AI summary + (once ready) the quit-risk score. This is the emotional payoff screen — give it real design time, not leftover time.

14. Live-updating risk score (optional)

Only build the animated/real-time (websocket) version if you're comfortably ahead of schedule by Day 5. Otherwise a score that updates on refresh is safer and still effective.

15–16. Voice note capture + auto-tag suggestion

Stretch goal only. Web Speech API in-browser is the fast path. Skip entirely if behind schedule — text + tags alone fully satisfy the product.

17. Momentum score

Show credit for partial progress on quit items, not just failure — reframes the dashboard from purely negative to balanced.

18. Comparison mode

Show a new item next to the most similar past attempts, using Dev B's retrieval output, so the risk prediction feels grounded rather than arbitrary.

19. One-tap re-commit

Let a user instantly downgrade a quit item into an easier version instead of just closing it out — shows product thinking beyond tracking failure.

Shareable pattern card + landing page

An auto-generated shareable image of a user's top insight, for organic growth. Plus a simple public landing page and demo GIF for the Product Hunt launch.

# Your 7-Day Timeline

| Day | Focus | Tasks |
| --- | --- | --- |
| Day 1 | App shell & mocked UI | Scaffold the React app: routing, layout, static log/quit UI against mocked data, using the shared API contract from Dev A. |
| Day 2 | Real core loop | Connect the reason-capture flow to real backend endpoints. Ensure add item → quit item → capture reason works end-to-end with zero friction. |
| Day 3 | Dashboard v1 | Build the pattern dashboard UI against real stats + AI summary endpoints. Start the quit-risk score UI once Dev B's endpoint is ready. |
| Day 4 | Depth features | Build momentum score and comparison mode using Dev B's retrieval output. Begin the public landing page for the launch phase. |
| Day 5 | Growth surfaces | Build the shareable pattern card. Finish the landing page and demo GIF. Add one-tap re-commit. Decide go/no-go on live-updating risk score. |
| Day 6 | Polish & mobile | Full visual polish pass — this most affects judge first impressions in a 3-minute demo. Fix mobile layout breaks; test on a real phone. |
| Day 7 | Demo & Product Hunt | Full team dry run of the live demo script against a clock. Finalize Product Hunt page copy, tagline, and first comment. |

# Coordination Notes

- The 10-second reason-capture flow is the single most important UX surface in the product — protect its simplicity even as other features get added around it.

- Build dashboard UI against Dev A's mocked endpoint shapes from Day 1 so you're never blocked waiting on the backend or AI layer.

- Own the Product Hunt and landing-page assets starting Day 4 — this is calendar-time-dependent work, not just coding hours, so start early.